## Issues Report
Title | Description | Issue ID | URL | State | Assignee | Created At | Due Date | Milestone | Labels | Functions/Screens
Add more funcionalities to Site navigation Menu | Add more functionality to the Site navigation Menu (Manage Room Registration, Manage Electricity/Water Bill) | 1 | Add more funcionalities to Site navigation Menu · Issue #4 | Closed | TanNV | 2023-05-15 | 2023-05-20 | iter2 | Task, 3_Done | Landing Page
Manage Profile ID issue | User is able to modify their ID when they shouldn't be able to | 2 | Manage Profile ID issue · Issue #5 | Closed | HungPN | 2023-05-18 | 2023-05-21 | iter2 | Defect, 3_Done | Manage Profile
Update Room Search function | Update to perform search on all fields | 3 | Update Room Search function · Issue #6 | Closed | KietNHG | 2023-05-27 | 2023-05-29 | iter2 | Task, 3_Done | View All Rooms
Add "Removed" status to Registrations | Add "Removed" status to indicate a user removed their registration | 4 | Add "Removed" status to Registrations · Issue #7 | Closed | KietNHG | 2023-05-28 | 2023-05-30 | iter3 | Task, 3_Done | Manage Room Registration
Add more notification functionality | Add "View all notifications" and "View single notification" to Landing page | 5 | Add more notification functionality · Issue #8 | Closed | TrieuDTH | 2023-06-18 | 2023-06-20 | iter4 | Task, 3_Done | Landing Page
Roommates are fetched incorrectly | Roommate information is fetched from all time instead of this semester only | 6 | Roommates are fetched incorrectly · Issue #9 | Closed | KietNHG | 2023-06-28 | 2023-06-30 | iter4 | Defect, 3_Done | View All Rooms
Statistics are fetched incorrectly | Statistics are fetched from all time instead of this semester only | 7 | Statistics are fetched incorrectly · Issue #10 | Closed | KietNHG | 2023-07-03 | 2023-07-07 | iter4 | Defect, 3_Done | View Statistics