## Project
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | Landing Page | Site Navigation | Guest, User, Manager | The user will be able to navigate the webpage using the menu on the left sidebar | Văn Tân | Updated | iter1 | iter2 | Now has more functions added to the menu
2 | Landing Page | View Notifications | Guest, User, Manager | The user can view the 2 most recent notifications on the landing page | Hải Triều | Updated | iter3 | iter4 | Now has button to view all notifications
3 | Dorm Rules Page | View Dorm Rules | Guest, User, Manager | This is a screen where the user can view the dorm rules | Văn Tân | Done | iter1 | none
4 | Contacts Page | Contact Manager by Email | Guest, User, Manager | This is a screen where the user can send an email to the managers by filling in the form on the page. | Hải Thy | Done | iter1 | none
5 | View All Notifications Page | View All Notifications | Guest, User, Manager | This is a screen where the user can view the titles of all past dorm notifications and are able to click on the title to view the contents of the notifications | Hải Triều | Done | iter4 | none
6 | View Single Notification Page | View Single Notification | Guest, User, Manager | This is a screen where the user can view the contents of a particular notification | Hải Triều | Done | iter4 | none
7 | User Login | Common | User, Manager | This is a screen which allows the user to enter email & password to login; on this page, there are also links for user to register new account or reset the password in casethey forget it | Ngọc Hùng | Done | iter1 | none
8 | User Register | Common | Guest | This is a screen which allows the user to create a new account using their roll ID as the username and inouts their password | Hải Thy | Done | iter1 | none
9 | Change Password | Common | User, Manager | This is a screen which allows the user to change their password by inputting their old and new passwords | Hải Thy | Done | iter1 | none
10 | Manage Profile | Common | User, Manager | This is a screen which allows the user to manage their own profile | Ngọc Hùng | Updated | iter1 | iter2 | Now cannot modify ID fields
11 | Logout | Common | User, Manager | Allows the user to logout of the Fdorm system | Hải Thy | Done | iter1 | none
12 | View All Rooms | Search for Room | User | This is a screen which allows the user to search for a room by size, gender, max numver of attendees, max price and whether the room has air-conditioning or view all available rooms | Gia Kiệt | Updated | iter1 | iter2 | Now perform search for all fields and improve SQL for searching
13 | View All Rooms | Register Room | User | The user can choose to register to one of the rooms on the search result | Gia Kiệt | Done | iter2 | none
14 | View All Rooms | View Roommates | User | If the user is already living in a room, they can click the link to view all their roommates' informations | Gia Kiệt | Updated | iter3 | iter4 | Now correctly fetch data from this semester only
15 | View Room Bills | View and Pay Rent Bill | User | The user can pay for one of the rooms they registered; cannot be accessed if they have already paid | Hải Thy | Done | iter3 | none
16 | View Electric and Water Bills | View and Pay Electric and Water Bills | User | The user can pay for their registered room's electricity and water bills | Hải Thy | Done | iter4 | none
17 | Send Complaints/Requests | Send Complaints or Request | User | The user can send a complaint or request email to the managers by filling in the form | Ngọc Hùng | Done | iter3 | none
18 | Send Complaints/Requests | Send Change Room Request | User | The user can send a request to change room with another student | Ngọc Hùng | Done | iter3 | none
19 | View Register History | View Register Room History | User | This is a screen where the user can view their room registrations and/or cancel a current pending registration | Gia Kiệt | Done | iter3 | none
20 | Manage Notifications | Manage All Notifications | Manager | This is the screen where the user can manage (add/view/update/delete) current notifications that are displayed on the landing page | Hải Triều | Done | iter3 | none
21 | Manage Notifications | Add Notification | Manager | This is a screen that allows the user to add a new notification (title - content - image) | Hải Triều | Done | iter4 | none
22 | Manage Notifications | Update Notification | Manager | This is a screen that allows the user to update an existing notification (title - content - image) | Hải Triều | Done | iter4 | none
23 | Manage Students | View All Students | Manager | This is a screen where the user can view all students that have registered an account in the Fdorm system | Hải Thy | Done | iter2 | none
24 | Manage Students | Update Student Information | Manager | This is a screen where the user can update a student's account informations | Hải Thy | Done | iter2 | none
25 | Manage Room | View All Rooms | Manager | This is the screen where the user can manage (add/view/update/delete) the rooms in the dorm | Gia Kiệt | Done | iter1 | none
26 | Manage Room | Add Room | Manager | This is a screen where the user can add a room's information into the database | Ngọc Hùng | Done | iter2 | none
27 | Manage Room | Update Room | Manager | This is a screen where the user can update a room's information | Ngọc Hùng | Done | iter2 | none
28 | Manage Room Registration | Manage Room Registration | Manager | This is a screen where the user can view all students' room registrations and their status and approve/reject them | Gia Kiệt | Updated | iter2 | iter3 | Added "Removed" registration status
29 | Manage Electric/Water Bills | Manage Electric/Water Bills | Manager | This is a screen where the user can manage (add/view/update/delete) an electric and water bill for a room | Ngọc Hùng | Done | iter4 | none
30 | Manage Electric/Water Bills | Add Electric/Water Bills | Manager | This is a screen where the user can add an electric and water bill for a room | Ngọc Hùng | Done | iter4 | none
31 | Manage Electric/Water Bills | Update Electric/Water Bills | Manager | This is a screen where the user can update an electric and water bill for a room | Ngọc Hùng | Done | iter4 | none
32 | View Requests | View Change Room Requests | Manager | This is a screen where the user can view and approve/reject all pending change room requests from students | Ngọc Hùng | Done | iter3 | none
33 | View Statistics | View Statistics | Manager | This is a screen where the user can view all current statistics of the dormitory | Gia Kiệt | Updated | iter3 | iter4 | Now correctly fetch data from this semester only

## Iter1
Iteration Tracking - Iteration 1
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Landing Page | Site Navigation | The user will be able to navigate the webpage using the menu on the left sidebar | Văn Tân | Done
2 | Dorm Rules Page | View Dorm Rules | This is a screen where the user can view the dorm rules | Văn Tân | Done
3 | Contacts Page | Contact Manager by Email | This is a screen where the user can send an email to the managers by filling in the form on the page. | Hải Thy | Done
4 | User Login | Common | This is a screen which allows the user to enter email & password to login; on this page, there are also links for user to register new account or reset the password in casethey forget it | Ngọc Hùng | Done
5 | User Register | Common | This is a screen which allows the user to create a new account using their roll ID as the username and inouts their password | Hải Thy | Done
6 | Change Password | Common | This is a screen which allows the user to change their password by inputting their old and new passwords | Hải Thy | Done
7 | Manage Profile | Common | This is a screen which allows the user to manage their own profile | Ngọc Hùng | Done
8 | Logout | Common | Allows the user to logout of the Fdorm system | Hải Thy | Done
9 | View All Rooms | Search for Room | This is a screen which allows the user to search for a room by size, gender, max numver of attendees, max price and whether the room has air-conditioning or view all available rooms | Gia Kiệt | Done
10 | View All Rooms | Register Room | The user can choose to register to one of the rooms on the search result | Gia Kiệt | Doing
11 | Manage Room | View All Rooms | This is a screen which allows the user to search for a room by size, gender, max numver of attendees, max price and whether the room has air-conditioning or view all available rooms | Gia Kiệt | Done
12 | Manage Room | Add Room | This is a screen where the user can add a room's information into the database | Ngọc Hùng | Doing
13 | Manage Room | Update Room | This is a screen where the user can update a room's information | Ngọc Hùng | Doing
14 | Manage Room Registration | Manage Room Registration | This is a screen where the user can view all students' room registrations and their status and approve/reject them | Gia Kiệt | Doing
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter2
Iteration Tracking - Iteration 2
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Landing Page | Site Navigation | The user will be able to navigate the webpage using the menu on the left sidebar | Văn Tân | Updated |  |  | Now has more functions added to the menu
2 | Landing Page | View Notifications | The user can view the 2 most recent notifications on the landing page | Hải Triều | Doing
3 | Manage Notifications | Manage All Notifications | This is the screen where the user can manage (add/view/update/delete) current notifications that are displayed on the landing page | Hải Triều | Doing
4 | Manage Profile | Common | This is a screen which allows the user to manage their own profile | Ngọc Hùng | Updated |  |  | Now cannot modify ID fields
5 | View All Rooms | Search for Room | This is a screen which allows the user to search for a room by size, gender, max numver of attendees, max price and whether the room has air-conditioning or view all available rooms | Gia Kiệt | Updated |  |  | Now perform search for all fields and improve SQL for searching
6 | View All Rooms | Register Room | The user can choose to register to one of the rooms on the search result | Gia Kiệt | Done
7 | Manage Students | View All Students | This is a screen where the user can add a room's information into the database | Hải Thy | Done
8 | Manage Students | Update Student Information | This is a screen where the user can update a room's information | Hải Thy | Done
9 | Manage Room | Add Room | This is a screen where the user can add a room's information into the database | Ngọc Hùng | Done
10 | Manage Room | Update Room | This is a screen where the user can update a room's information | Ngọc Hùng | Done
11 | Manage Room Registration | Manage Room Registration | This is a screen where the user can view all students' room registrations and their status and approve/reject them | Gia Kiệt | Done
12 | View Requests | View Change Room Requests | This is a screen where the user can view and approve/reject all pending change room requests from students | Ngọc Hùng | Doing
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter3
Iteration Tracking - Iteration 3
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Landing Page | View Notifications | The user can view the 2 most recent notifications on the landing page | Hải Triều | Done
2 | Manage Notifications | Manage All Notifications | This is the screen where the user can manage (add/view/update/delete) current notifications that are displayed on the landing page | Hải Triều | Done
3 | View All Rooms | View Roommates | If the user is already living in a room, they can click the link to view all their roommates' informations | Gia Kiệt | Done |  |  | Now cannot modify ID fields
4 | View Room Bills | View and Pay Rent Bill | The user can pay for one of the rooms they registered; cannot be accessed if they have already paid | Hải Thy | Done |  |  | Now perform search for all fields and improve SQL for searching
5 | View Electric and Water Bills | View and Pay Electric and Water Bills | The user can pay for their registered room's electricity and water bills | Hải Thy | Doing
6 | Send Complaints/Requests | Send Complaints or Request | The user can send a complaint or request email to the managers by filling in the form | Ngọc Hùng | Done
7 | Send Complaints/Requests | Send Change Room Request | The user can send a request to change room with another student | Ngọc Hùng | Done
8 | View Register History | View Register Room History | This is a screen where the user can view their room registrations and/or cancel a current pending registration | Gia Kiệt | Done
9 | Manage Notifications | Manage All Notifications | This is the screen where the user can manage (add/view/update/delete) current notifications that are displayed on the landing page | Hải Triều | Done
10 | Manage Notifications | Add Notification | This is a screen that allows the user to add a new notification (title - content - image) | Hải Triều | Done
11 | Manage Room Registration | Manage Room Registration | This is a screen where the user can view and approve/reject all pending change room requests from students | Gia Kiệt | Updated |  |  | Added "Removed" registration status
12 | View Requests | View Change Room Requests | This is a screen where the user can view and approve/reject all pending change room requests from students | Ngọc Hùng | Done
13 | View Statistics | View Statistics | This is a screen where the user can view all current statistics of the dormitory | Gia Kiệt | Done
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter4
Iteration Tracking - Iteration 4
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Landing Page | View Notifications | The user can view the 2 most recent notifications on the landing page | Hải Triều | Updated |  |  | Now has button to view all notifications
2 | View All Notifications Page | View All Notifications | This is a screen where the user can view the titles of all past dorm notifications and are able to click on the title to view the contents of the notifications | Hải Triều | Done
3 | View Single Notification Page | View Single Notification | This is a screen where the user can view the contents of a particular notification | Hải Triều | Done
4 | Manage Notifications | Add Notification | This is a screen that allows the user to add a new notification (title - content - image) | Hải Triều | Done |  |  | Now correctly fetch data from this semester only
5 | Manage Notifications | Update Notification | This is a screen that allows the user to update an existing notification (title - content - image) | Hải Triều | Done
6 | View All Rooms | View Roommates | If the user is already living in a room, they can click the link to view all their roommates' informations | Gia Kiệt | Updated |  |  | Now correctly fetch data from this semester only
7 | View Electric and Water Bills | View and Pay Electric and Water Bills | The user can pay for their registered room's electricity and water bills | Hải Thy | Done
8 | Manage Electric/Water Bills | Manage Electric/Water Bills | This is a screen where the user can manage (add/view/update/delete) an electric and water bill for a room | Ngọc Hùng | Done
9 | Manage Electric/Water Bills | Add Electric/Water Bills | This is a screen where the user can add an electric and water bill for a room | Ngọc Hùng | Done
10 | Manage Electric/Water Bills | Update Electric/Water Bills | This is a screen where the user can update an electric and water bill for a room | Ngọc Hùng | Done
11 | View Statistics | View Statistics | This is a screen where the user can view all current statistics of the dormitory | Gia Kiệt | Updated |  |  | Now correctly fetch data from this semester only
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document